## Sheet1
CSI5380: Kill-9 Project Plan |  |  |  | Sprint 1 2015-10-09 | Sprint 2 2015-16-09 | Sprint 3 2015-10-23 | Dependencies
1 | Planning | [6 empty] | Team
| 1.1 | Project Plan |  |  | MBP |  |  | CTI | Cynthia Torkuma Ikongo
[8 empty] | JS | Jiaren Suo
[8 empty] | KZ | Kaifan Zhu
[8 empty] | MBP | Michele Belanger-Petrucci
2 | Design | [6 empty] | YL | Yuan Liu
| 2.1 | Architecture document |  |  | MBP
| 2.2 | Use Case document |  | MBP
| 2.3 | View design
| 2.4 | Model design
| 2.5 | Controller design
| 2.6 | DAO design
| 2.7 | Database design
| 2.8 | Quality assurance framework design |  | MBP
2.9
3
3.1
3.2
3.3
3.4
3 | Development | [5 empty] | 2.1, 2.2, 2.3
| 3.1 | Implement Views
|  | 3.11 | Home Page
|  | 3.12 | Login
|  | 3.13 | Registration
|  | 3.14 | Header
|  | 3.15 | Shopping cart
|  | 3.16 | Checkout
|  | 3.17 | Account
|  | 3.18 | Order Detail
|  | 3.19 | Item Detail
|  | 3.2 | Order Confirmation
|  | 3.21 | Credit Verification Failure
|  | 3.22 | Error
| 3.2 | Implement Controllers
|  | 3.21 | Implement Controller 1
3.22
3.23
3.24
3.25
3.26
3.27
3.28
| 3.3 | Implement Model
|  | 3.31 | Implement WS1
|  | 3.32 | Implement WS2
3.33
3.34
3.35
3.36
3.37
|  | 3.38 | Implement DAO
| 3.4 | Implement Database
3.5
4 | Test
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8